## BidAnalysis
Bid Analysis Demo.xlsx
James W. Richardson
© 2011
Chapter 14
BId Analysis with Simulation is demonstrated for a general contractor bidding a new building.
Probability Distribution for Costs
Cost Categories |  |  | Cost |  | Minimum | Average | Maximum | Std. Dev.
(formulas in D or E)
Site preparation (clear trees) |  |  | 799.5148 | =UNIFORM(G11,I11) | 500 |  | 1000
Water meter fee |  |  | 500 | =H12 |  | 500
Electrical poles & hookup |  |  | 245.8797 | =GRK(G13,H13,I13,UNIFORM()) | 150 | 250 | 500
Sand and gravel |  |  | 1980.3151 | =GRK(G15,H15,I15,UNIFORM()) | 1000 | 2000 | 3000
Forms |  |  | 3700.2634 | =GRK(G16,H16,I16,UNIFORM()) | 2000 | 4000 | 5000
Plumbing and plumbers |  |  | 7384.2045 | =GRK(G17,H17,I17,UNIFORM()) | 4000 | 5000 | 7000
Foundation concrete |  |  | 9890.1789 | =GRK(G18,H18,I18,UNIFORM()) | 8000 | 10000 | 12000
Lumber and windows |  |  | 4805.4122 | =GRK(G20,H20,I20,UNIFORM()) | 4500 | 5000 | 6000
Framers |  |  | 26290.3805 | =GRK(G21,H21,I21,UNIFORM()) | 22000 | 25000 | 29000
Electrical |  |  | 3175.0922 | =GRK(G22,H22,I22,UNIFORM()) | 2500 | 3000 | 3500
Bricks |  |  | 8840.419 | =GRK(G23,H23,I23,UNIFORM()) | 7500 | 8000 | 9000
Brick layers |  |  | 8311.5614 | =GRK(G24,H24,I24,UNIFORM()) | 6000 | 10000 | 11000
Roofers and shingles |  |  | 7556.9029 | =GRK(G25,H25,I25,UNIFORM()) | 6000 | 7500 | 7900
Concrete flat work |  |  | 2399.1647 | =GRK(G27,H27,I27,UNIFORM()) | 2000 | 2500 | 3000
Sheetrock |  |  | 2067.6648 | =GRK(G28,H28,I28,UNIFORM()) | 1800 | 2000 | 2200
Sheetrockers |  |  | 4902.2529 | =GRK(G29,H29,I29,UNIFORM()) | 4000 | 5000 | 5500
Trim carpenters |  |  | 26417.7915 | =GRK(G30,H30,I30,UNIFORM()) | 20000 | 25000 | 40000
Plumbers and fixtures |  |  | 13551.6434 | =GRK(G31,H31,I31,UNIFORM()) | 12000 | 15000 | 17000
Painters & paint/varnish |  |  | 12725.7487 | =GRK(G32,H32,I32,UNIFORM()) | 12000 | 14000 | 16000
Wallpaper & installation |  |  | 4217.9012 | =GRK(G33,H33,I33,UNIFORM()) | 3000 | 4000 | 4500
Landscaping |  |  | 4275.7229 | =GRK(G34,H34,I34,UNIFORM()) | 1000 | 5000 | 10000
Floor coverings |  |  | 6410.7531 | =GRK(G36,H36,I36,UNIFORM()) | 5000 | 6000 | 8000
Doors and fixtures |  |  | 6066.9446 | =GRK(G37,H37,I37,UNIFORM()) | 4000 | 6000 | 9000
Construction interest |  | 0.083274 | 5683.8512 | =NORM(H39,J39) |  | 0.08 |  | 0.005
Days to Completion |  | 149.6132 |  | =GRK(G40,H40,I40,UNIFORM()) | 140 | 160 | 220
Sum of Cash Costs |  |  | 172199.5635
Contractor's profits |  |  | 25000 |  |  |  |  | Scenario Table for Evaluating Alternative Bids
[6 empty] | Bid Amount |  | Bid 1 | Bid 2 | Bid 3 | Bid 4
Total Cost (KOV) |  | TC | 197199.5635 |  |  | 190000 |  | 190000 | 195000 | 200000 | 205000
Cost overrun or profit losses (KOV) |  |  | 7199.5635 |  | Formula for Cost Over Run
=IF(E45>H45,(E45-H45),0)
Simetar Simulation Results for 100 Iterations. 3:20:49 PM 12/10/00 (1.70sec). | [5 empty] | Simetar Simulation Results for 100 Iterations. 3:16:21 PM 12/10/00 (6.92sec).
| $E$45 | [5 empty] | $E$47 | $E$47 | $E$47 | $E$47
| Total Cost | [5 empty] | Bid 1 | Bid 2 | Bid 3 | Bid 4
Mean | 198525.2128 |  |  |  |  | Mean | 8879.2276 | 4951.5595 | 2331.696 | 930.1389
StDev | 7327.6698 |  |  |  |  | StDev | 6797.7771 | 5665.7643 | 3996.0033 | 2187.6674
CV | 3.6911 |  |  |  |  | CV | 76.5582 | 114.4238 | 171.3775 | 235.1979
Min | 185196.714 |  |  |  |  | Min | 0 | 0 | 0 | 0
Max | 214763.1164 |  |  |  |  | Max | 24763.1164 | 19763.1164 | 14763.1164 | 9763.1164
Probabilities of Cost Overruns Greater Than Selected Targets
[8 empty] | Bid 1 | Bid 2 | Bid 3 | Bid 4
Probability of a Cost Overrun
[7 empty] | Target 1 | 0 | 0 | 0 | 0
[7 empty] | Prob<=T1 | 0.87 | 0.67 | 0.37 | 0.21
Probability of a $5,000 or Greater Overrun
[7 empty] | Target 2 | 5000 | 5000 | 5000 | 5000
[7 empty] | Prob<=T2 | 0.66536 | 0.36067 | 0.20467 | 0.064927
Probability of a $10,000 or Greater Overrun
[7 empty] | Target 3 | 10000 | 10000 | 10000 | 10000
[7 empty] | Prob<=T3 | 0.36067 | 0.20467 | 0.064927 | 0
Probability of a $15,000 or Greater Overrun
[7 empty] | Target 4 | 15000 | 15000 | 15000 | 15000
[7 empty] | Prob<=T4 | 0.20467 | 0.064927 | 0 | 0
Probability of a $20,000 or Greater Overrun
[7 empty] | Target 5 | 20000 | 20000 | 20000 | 20000
[7 empty] | Prob<=T5 | 0.064927 | 0 | 0 | 0

## SimData
Simetar Simulation Results for 100 Iterations. 4:56:34 PM 3/27/2005 (0.57 sec.). © 2005.
Variable | BidAnalysis!E45
Mean | 203786.3409
StDev | 18258.7925
CV | 8.9598
Min | 170609.8403
Max | 244510.4758
Iteration | TC
1 | 178423.361
2 | 215253.1995
3 | 181666.9331
4 | 203055.3024
5 | 184918.7055
6 | 190640.4169
7 | 177754.142
8 | 222145.5326
9 | 174216.3639
10 | 226394.9859
11 | 220642.8205
12 | 207315.5143
13 | 197981.3289
14 | 206532.7014
15 | 226601.7734
16 | 189226.5728
17 | 212983.6451
18 | 229460.937
19 | 209923.2894
20 | 230581.1152
21 | 189760.6989
22 | 202680.6561
23 | 211620.0427
24 | 211932.3749
25 | 212385.035
26 | 204213.4542
27 | 215242.5044
28 | 201861.4964
29 | 182980.062
30 | 188643.1903
31 | 213105.8714
32 | 228504.982
33 | 191206.1935
34 | 222305.0007
35 | 227615.8008
36 | 214909.2482
37 | 223498.1907
38 | 228718.2365
39 | 188222.662
40 | 232845.59
41 | 183880.2279
42 | 223698.4165
43 | 198336.5235
44 | 190339.5599
45 | 205695.4201
46 | 204291.5742
47 | 191521.9995
48 | 188546.0538
49 | 208216.126
50 | 213415.5705
51 | 235467.4705
52 | 208245.8361
53 | 238199.8181
54 | 181189.9989
55 | 182261.0292
56 | 187012.8267
57 | 180238.9333
58 | 233936.2133
59 | 195118.5133
60 | 191830.6316
61 | 184503.595
62 | 221321.3045
63 | 230759.3247
64 | 244510.4758
65 | 198393.3257
66 | 180420.4452
67 | 189449.3398
68 | 195087.6194
69 | 220402.532
70 | 197172.7825
71 | 207105.3235
72 | 199094.3594
73 | 180814.5894
74 | 224868.1129
75 | 171228.729
76 | 227360.219
77 | 182605.0145
78 | 224160.0607
79 | 212830.6849
80 | 186908.2942
81 | 184883.5114
82 | 170609.8403
83 | 225144.0949
84 | 203505.0735
85 | 193247.1633
86 | 193738.5592
87 | 203766.3123
88 | 195944.4623
89 | 206332.371
90 | 171967.0727
91 | 213483.0636
92 | 219716.4804
93 | 178747.8383
94 | 219465.9498
95 | 190572.7862
96 | 230886.7804
97 | 193097.2668
98 | 215270.7032
99 | 188346.0544
100 | 181499.8952
x1-value
Prob(X<=x1)
x2-value
Prob(X<=x2)
x3-value
Prob(X<=x3)
x4-value
Prob(X<=x4)
x5-value
Prob(X<=x5)

## CostOverRun
Simetar Simulation Results for 100 Iterations. 3:16:21 PM 12/10/00 (6.92sec). © 2000 Texas Agricultural Experiment Station.
| [demoprojetanalysis.xls]Sheet1!$E$47 | [demoprojetanalysis.xls]Sheet1!$E$47 | [demoprojetanalysis.xls]Sheet1!$E$47 | [demoprojetanalysis.xls]Sheet1!$E$47
Mean | 8879.2276 | 4951.5595 | 2331.696 | 930.1389
StDev | 6797.7771 | 5665.7643 | 3996.0033 | 2187.6674
CV | 76.5582 | 114.4238 | 171.3775 | 235.1979
Min | 0 | 0 | 0 | 0
Max | 24763.1164 | 19763.1164 | 14763.1164 | 9763.1164
Iteration | Bid 1 | Bid 2 | Bid 3 | Bid 4 | Bid 1 | CDFProb. | Bid 2 | CDFProb. | Bid 3 | CDFProb. | Bid 4 | CDFProb.
1 | 8906.6855 | 3906.6855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 5371.5594 | 371.5594 | 0 | 0 | 0 | 0.010101 | 0 | 0.010101 | 0 | 0.010101 | 0 | 0.010101
3 | 12567.061 | 7567.061 | 2567.061 | 0 | 0 | 0.020202 | 0 | 0.020202 | 0 | 0.020202 | 0 | 0.020202
4 | 23391.4612 | 18391.4612 | 13391.4612 | 8391.4612 | 0 | 0.030303 | 0 | 0.030303 | 0 | 0.030303 | 0 | 0.030303
5 | 17217.8764 | 12217.8764 | 7217.8764 | 2217.8764 | 0 | 0.040404 | 0 | 0.040404 | 0 | 0.040404 | 0 | 0.040404
6 | 9178.6977 | 4178.6977 | 0 | 0 | 0 | 0.050505 | 0 | 0.050505 | 0 | 0.050505 | 0 | 0.050505
7 | 7449.6164 | 2449.6164 | 0 | 0 | 0 | 0.060606 | 0 | 0.060606 | 0 | 0.060606 | 0 | 0.060606
8 | 0 | 0 | 0 | 0 | 0 | 0.070707 | 0 | 0.070707 | 0 | 0.070707 | 0 | 0.070707
9 | 17262.7878 | 12262.7878 | 7262.7878 | 2262.7878 | 0 | 0.080808 | 0 | 0.080808 | 0 | 0.080808 | 0 | 0.080808
10 | 5719.1146 | 719.1146 | 0 | 0 | 0 | 0.090909 | 0 | 0.090909 | 0 | 0.090909 | 0 | 0.090909
11 | 16097.6275 | 11097.6275 | 6097.6275 | 1097.6275 | 0 | 0.10101 | 0 | 0.10101 | 0 | 0.10101 | 0 | 0.10101
12 | 856.264 | 0 | 0 | 0 | 0 | 0.11111 | 0 | 0.11111 | 0 | 0.11111 | 0 | 0.11111
13 | 10447.9098 | 5447.9098 | 447.9098 | 0 | 0 | 0.12121 | 0 | 0.12121 | 0 | 0.12121 | 0 | 0.12121
14 | 6181.7471 | 1181.7471 | 0 | 0 | 778.8112 | 0.13131 | 0 | 0.13131 | 0 | 0.13131 | 0 | 0.13131
15 | 13150.696 | 8150.696 | 3150.696 | 0 | 856.264 | 0.14141 | 0 | 0.14141 | 0 | 0.14141 | 0 | 0.14141
16 | 14040.9854 | 9040.9854 | 4040.9854 | 0 | 1264.084 | 0.15152 | 0 | 0.15152 | 0 | 0.15152 | 0 | 0.15152
17 | 20777.6934 | 15777.6934 | 10777.6934 | 5777.6934 | 1319.9836 | 0.16162 | 0 | 0.16162 | 0 | 0.16162 | 0 | 0.16162
18 | 0 | 0 | 0 | 0 | 1450.0401 | 0.17172 | 0 | 0.17172 | 0 | 0.17172 | 0 | 0.17172
19 | 19435.5221 | 14435.5221 | 9435.5221 | 4435.5221 | 1648.5601 | 0.18182 | 0 | 0.18182 | 0 | 0.18182 | 0 | 0.18182
20 | 4182.1379 | 0 | 0 | 0 | 1681.0209 | 0.19192 | 0 | 0.19192 | 0 | 0.19192 | 0 | 0.19192
21 | 6131.1722 | 1131.1722 | 0 | 0 | 2372.9555 | 0.20202 | 0 | 0.20202 | 0 | 0.20202 | 0 | 0.20202
22 | 9392.7217 | 4392.7217 | 0 | 0 | 2832.7744 | 0.21212 | 0 | 0.21212 | 0 | 0.21212 | 0 | 0.21212
23 | 1648.5601 | 0 | 0 | 0 | 2952.3322 | 0.22222 | 0 | 0.22222 | 0 | 0.22222 | 0 | 0.22222
24 | 24763.1164 | 19763.1164 | 14763.1164 | 9763.1164 | 3024.102 | 0.23232 | 0 | 0.23232 | 0 | 0.23232 | 0 | 0.23232
25 | 7109.0877 | 2109.0877 | 0 | 0 | 3318.0829 | 0.24242 | 0 | 0.24242 | 0 | 0.24242 | 0 | 0.24242
26 | 10916.2432 | 5916.2432 | 916.2432 | 0 | 3744.5298 | 0.25253 | 0 | 0.25253 | 0 | 0.25253 | 0 | 0.25253
27 | 1450.0401 | 0 | 0 | 0 | 4074.7498 | 0.26263 | 0 | 0.26263 | 0 | 0.26263 | 0 | 0.26263
28 | 18609.365 | 13609.365 | 8609.365 | 3609.365 | 4076.4475 | 0.27273 | 0 | 0.27273 | 0 | 0.27273 | 0 | 0.27273
29 | 8518.0906 | 3518.0906 | 0 | 0 | 4169.6787 | 0.28283 | 0 | 0.28283 | 0 | 0.28283 | 0 | 0.28283
30 | 5384.3676 | 384.3676 | 0 | 0 | 4182.1379 | 0.29293 | 0 | 0.29293 | 0 | 0.29293 | 0 | 0.29293
31 | 7361.8939 | 2361.8939 | 0 | 0 | 4667.9438 | 0.30303 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0.30303
32 | 15286.5543 | 10286.5543 | 5286.5543 | 286.5543 | 4674.3954 | 0.31313 | 0 | 0.31313 | 0 | 0.31313 | 0 | 0.31313
33 | 16560.0818 | 11560.0818 | 6560.0818 | 1560.0818 | 4677.9069 | 0.32323 | 0 | 0.32323 | 0 | 0.32323 | 0 | 0.32323
34 | 7600.3885 | 2600.3885 | 0 | 0 | 5371.5594 | 0.33333 | 371.5594 | 0.33333 | 0 | 0.33333 | 0 | 0.33333
35 | 0 | 0 | 0 | 0 | 5384.3676 | 0.34343 | 384.3676 | 0.34343 | 0 | 0.34343 | 0 | 0.34343
36 | 11885.8486 | 6885.8486 | 1885.8486 | 0 | 5494.2954 | 0.35354 | 494.2954 | 0.35354 | 0 | 0.35354 | 0 | 0.35354
37 | 6611.2819 | 1611.2819 | 0 | 0 | 5719.1146 | 0.36364 | 719.1146 | 0.36364 | 0 | 0.36364 | 0 | 0.36364
38 | 18996.9489 | 13996.9489 | 8996.9489 | 3996.9489 | 5983.5383 | 0.37374 | 983.5383 | 0.37374 | 0 | 0.37374 | 0 | 0.37374
39 | 4169.6787 | 0 | 0 | 0 | 6131.1722 | 0.38384 | 1131.1722 | 0.38384 | 0 | 0.38384 | 0 | 0.38384
40 | 5983.5383 | 983.5383 | 0 | 0 | 6181.7471 | 0.39394 | 1181.7471 | 0.39394 | 0 | 0.39394 | 0 | 0.39394
41 | 12137.689 | 7137.689 | 2137.689 | 0 | 6396.5102 | 0.40404 | 1396.5102 | 0.40404 | 0 | 0.40404 | 0 | 0.40404
42 | 4674.3954 | 0 | 0 | 0 | 6574.0792 | 0.41414 | 1574.0792 | 0.41414 | 0 | 0.41414 | 0 | 0.41414
43 | 4074.7498 | 0 | 0 | 0 | 6611.2819 | 0.42424 | 1611.2819 | 0.42424 | 0 | 0.42424 | 0 | 0.42424
44 | 7963.0256 | 2963.0256 | 0 | 0 | 7109.0877 | 0.43434 | 2109.0877 | 0.43434 | 0 | 0.43434 | 0 | 0.43434
45 | 19156.0496 | 14156.0496 | 9156.0496 | 4156.0496 | 7313.5943 | 0.44444 | 2313.5943 | 0.44444 | 0 | 0.44444 | 0 | 0.44444
46 | 14362.517 | 9362.517 | 4362.517 | 0 | 7361.8939 | 0.45455 | 2361.8939 | 0.45455 | 0 | 0.45455 | 0 | 0.45455
47 | 9234.8771 | 4234.8771 | 0 | 0 | 7449.6164 | 0.46465 | 2449.6164 | 0.46465 | 0 | 0.46465 | 0 | 0.46465
48 | 11064.1633 | 6064.1633 | 1064.1633 | 0 | 7517.3781 | 0.47475 | 2517.3781 | 0.47475 | 0 | 0.47475 | 0 | 0.47475
49 | 14673.1127 | 9673.1127 | 4673.1127 | 0 | 7600.3885 | 0.48485 | 2600.3885 | 0.48485 | 0 | 0.48485 | 0 | 0.48485
50 | 19190.5443 | 14190.5443 | 9190.5443 | 4190.5443 | 7960.9961 | 0.49495 | 2960.9961 | 0.49495 | 0 | 0.49495 | 0 | 0.49495
51 | 3318.0829 | 0 | 0 | 0 | 7963.0256 | 0.50505 | 2963.0256 | 0.50505 | 0 | 0.50505 | 0 | 0.50505
52 | 2372.9555 | 0 | 0 | 0 | 8063.9373 | 0.51515 | 3063.9373 | 0.51515 | 0 | 0.51515 | 0 | 0.51515
53 | 19417.8854 | 14417.8854 | 9417.8854 | 4417.8854 | 8518.0906 | 0.52525 | 3518.0906 | 0.52525 | 0 | 0.52525 | 0 | 0.52525
54 | 4667.9438 | 0 | 0 | 0 | 8546.8829 | 0.53535 | 3546.8829 | 0.53535 | 0 | 0.53535 | 0 | 0.53535
55 | 0 | 0 | 0 | 0 | 8655.5951 | 0.54545 | 3655.5951 | 0.54545 | 0 | 0.54545 | 0 | 0.54545
56 | 778.8112 | 0 | 0 | 0 | 8902.8007 | 0.55556 | 3902.8007 | 0.55556 | 0 | 0.55556 | 0 | 0.55556
57 | 1681.0209 | 0 | 0 | 0 | 8906.6855 | 0.56566 | 3906.6855 | 0.56566 | 0 | 0.56566 | 0 | 0.56566
58 | 17860.5692 | 12860.5692 | 7860.5692 | 2860.5692 | 8944.5583 | 0.57576 | 3944.5583 | 0.57576 | 0 | 0.57576 | 0 | 0.57576
59 | 23893.5144 | 18893.5144 | 13893.5144 | 8893.5144 | 9038.6119 | 0.58586 | 4038.6119 | 0.58586 | 0 | 0.58586 | 0 | 0.58586
60 | 0 | 0 | 0 | 0 | 9178.6977 | 0.59596 | 4178.6977 | 0.59596 | 0 | 0.59596 | 0 | 0.59596
61 | 9479.2454 | 4479.2454 | 0 | 0 | 9234.8771 | 0.60606 | 4234.8771 | 0.60606 | 0 | 0.60606 | 0 | 0.60606
62 | 11505.637 | 6505.637 | 1505.637 | 0 | 9392.7217 | 0.61616 | 4392.7217 | 0.61616 | 0 | 0.61616 | 0 | 0.61616
63 | 4076.4475 | 0 | 0 | 0 | 9479.2454 | 0.62626 | 4479.2454 | 0.62626 | 0 | 0.62626 | 0 | 0.62626
64 | 1319.9836 | 0 | 0 | 0 | 10037.1009 | 0.63636 | 5037.1009 | 0.63636 | 37.1009 | 0.63636 | 0 | 0.63636
65 | 3744.5298 | 0 | 0 | 0 | 10447.9098 | 0.64646 | 5447.9098 | 0.64646 | 447.9098 | 0.64646 | 0 | 0.64646
66 | 6574.0792 | 1574.0792 | 0 | 0 | 10726.7431 | 0.65657 | 5726.7431 | 0.65657 | 726.7431 | 0.65657 | 0 | 0.65657
67 | 1264.084 | 0 | 0 | 0 | 10916.2432 | 0.66667 | 5916.2432 | 0.66667 | 916.2432 | 0.66667 | 0 | 0.66667
68 | 8063.9373 | 3063.9373 | 0 | 0 | 11064.1633 | 0.67677 | 6064.1633 | 0.67677 | 1064.1633 | 0.67677 | 0 | 0.67677
69 | 8902.8007 | 3902.8007 | 0 | 0 | 11319.5884 | 0.68687 | 6319.5884 | 0.68687 | 1319.5884 | 0.68687 | 0 | 0.68687
70 | 0 | 0 | 0 | 0 | 11505.637 | 0.69697 | 6505.637 | 0.69697 | 1505.637 | 0.69697 | 0 | 0.69697
71 | 7960.9961 | 2960.9961 | 0 | 0 | 11885.8486 | 0.70707 | 6885.8486 | 0.70707 | 1885.8486 | 0.70707 | 0 | 0.70707
72 | 16393.9646 | 11393.9646 | 6393.9646 | 1393.9646 | 12137.689 | 0.71717 | 7137.689 | 0.71717 | 2137.689 | 0.71717 | 0 | 0.71717
73 | 8546.8829 | 3546.8829 | 0 | 0 | 12567.061 | 0.72727 | 7567.061 | 0.72727 | 2567.061 | 0.72727 | 0 | 0.72727
74 | 18028.7755 | 13028.7755 | 8028.7755 | 3028.7755 | 12643.9692 | 0.73737 | 7643.9692 | 0.73737 | 2643.9692 | 0.73737 | 0 | 0.73737
75 | 12643.9692 | 7643.9692 | 2643.9692 | 0 | 13150.696 | 0.74747 | 8150.696 | 0.74747 | 3150.696 | 0.74747 | 0 | 0.74747
76 | 10037.1009 | 5037.1009 | 37.1009 | 0 | 13676.4538 | 0.75758 | 8676.4538 | 0.75758 | 3676.4538 | 0.75758 | 0 | 0.75758
77 | 7313.5943 | 2313.5943 | 0 | 0 | 14040.9854 | 0.76768 | 9040.9854 | 0.76768 | 4040.9854 | 0.76768 | 0 | 0.76768
78 | 0 | 0 | 0 | 0 | 14362.517 | 0.77778 | 9362.517 | 0.77778 | 4362.517 | 0.77778 | 0 | 0.77778
79 | 0 | 0 | 0 | 0 | 14673.1127 | 0.78788 | 9673.1127 | 0.78788 | 4673.1127 | 0.78788 | 0 | 0.78788
80 | 13676.4538 | 8676.4538 | 3676.4538 | 0 | 15286.5543 | 0.79798 | 10286.5543 | 0.79798 | 5286.5543 | 0.79798 | 286.5543 | 0.79798
81 | 8944.5583 | 3944.5583 | 0 | 0 | 16097.6275 | 0.80808 | 11097.6275 | 0.80808 | 6097.6275 | 0.80808 | 1097.6275 | 0.80808
82 | 0 | 0 | 0 | 0 | 16393.9646 | 0.81818 | 11393.9646 | 0.81818 | 6393.9646 | 0.81818 | 1393.9646 | 0.81818
83 | 6396.5102 | 1396.5102 | 0 | 0 | 16560.0818 | 0.82828 | 11560.0818 | 0.82828 | 6560.0818 | 0.82828 | 1560.0818 | 0.82828
84 | 7517.3781 | 2517.3781 | 0 | 0 | 17217.8764 | 0.83838 | 12217.8764 | 0.83838 | 7217.8764 | 0.83838 | 2217.8764 | 0.83838
85 | 9038.6119 | 4038.6119 | 0 | 0 | 17262.7878 | 0.84848 | 12262.7878 | 0.84848 | 7262.7878 | 0.84848 | 2262.7878 | 0.84848
86 | 20548.215 | 15548.215 | 10548.215 | 5548.215 | 17860.5692 | 0.85859 | 12860.5692 | 0.85859 | 7860.5692 | 0.85859 | 2860.5692 | 0.85859
87 | 11319.5884 | 6319.5884 | 1319.5884 | 0 | 18028.7755 | 0.86869 | 13028.7755 | 0.86869 | 8028.7755 | 0.86869 | 3028.7755 | 0.86869
88 | 0 | 0 | 0 | 0 | 18609.365 | 0.87879 | 13609.365 | 0.87879 | 8609.365 | 0.87879 | 3609.365 | 0.87879
89 | 21910.9913 | 16910.9913 | 11910.9913 | 6910.9913 | 18996.9489 | 0.88889 | 13996.9489 | 0.88889 | 8996.9489 | 0.88889 | 3996.9489 | 0.88889
90 | 2832.7744 | 0 | 0 | 0 | 19156.0496 | 0.89899 | 14156.0496 | 0.89899 | 9156.0496 | 0.89899 | 4156.0496 | 0.89899
91 | 3024.102 | 0 | 0 | 0 | 19190.5443 | 0.90909 | 14190.5443 | 0.90909 | 9190.5443 | 0.90909 | 4190.5443 | 0.90909
92 | 4677.9069 | 0 | 0 | 0 | 19417.8854 | 0.91919 | 14417.8854 | 0.91919 | 9417.8854 | 0.91919 | 4417.8854 | 0.91919
93 | 0 | 0 | 0 | 0 | 19435.5221 | 0.92929 | 14435.5221 | 0.92929 | 9435.5221 | 0.92929 | 4435.5221 | 0.92929
94 | 0 | 0 | 0 | 0 | 20548.215 | 0.93939 | 15548.215 | 0.93939 | 10548.215 | 0.93939 | 5548.215 | 0.93939
95 | 10726.7431 | 5726.7431 | 726.7431 | 0 | 20777.6934 | 0.94949 | 15777.6934 | 0.94949 | 10777.6934 | 0.94949 | 5777.6934 | 0.94949
96 | 8655.5951 | 3655.5951 | 0 | 0 | 21910.9913 | 0.9596 | 16910.9913 | 0.9596 | 11910.9913 | 0.9596 | 6910.9913 | 0.9596
97 | 0 | 0 | 0 | 0 | 23214.3416 | 0.9697 | 18214.3416 | 0.9697 | 13214.3416 | 0.9697 | 8214.3416 | 0.9697
98 | 5494.2954 | 494.2954 | 0 | 0 | 23391.4612 | 0.9798 | 18391.4612 | 0.9798 | 13391.4612 | 0.9798 | 8391.4612 | 0.9798
99 | 23214.3416 | 18214.3416 | 13214.3416 | 8214.3416 | 23893.5144 | 0.9899 | 18893.5144 | 0.9899 | 13893.5144 | 0.9899 | 8893.5144 | 0.9899
100 | 2952.3322 | 0 | 0 | 0 | 24763.1164 | 1 | 19763.1164 | 1 | 14763.1164 | 1 | 9763.1164 | 1
Probabilities of Cost Overruns Greater Than Selected Targets
[6 empty] | Target 1 | 0 | 0 | 0 | 0
[6 empty] | Prob<=T1 | 0.87 | 0.67 | 0.37 | 0.21
[6 empty] | Target 2 | 5000 | 5000 | 5000 | 5000
[6 empty] | Prob<=T2 | 0.66536 | 0.36067 | 0.20467 | 0.064927
[6 empty] | Target 3 | 10000 | 10000 | 10000 | 10000
[6 empty] | Prob<=T3 | 0.36067 | 0.20467 | 0.064927 | 0
[6 empty] | Target 4 | 15000 | 15000 | 15000 | 15000
[6 empty] | Prob<=T4 | 0.20467 | 0.064927 | 0 | 0
[6 empty] | Target 5 | 20000 | 20000 | 20000 | 20000
[6 empty] | Prob<=T5 | 0.064927 | 0 | 0 | 0