## Sheet1
Project Management Demo.xlsx
James W. Richardson
© 2011
Chapter 14
Project Management Analysis for Developing and Using a Simulation Model.
PDF for Time Expended
|  | Immediate | Time to | Start | End | Cost per | Total | Pessimistic | Expected | Optimistic | Formula for
No. | Project Activities | Predecessor | Complete | Time | Time | Time Unit | Cost | Minimum | Expected | Maximum | Start Time | End Time
1 | Develop Diagram of the System | 0 | 10.0563 | - | 10.0563 | 100 | 1005.6325 | 10 | 20 | 30 | - | =D10
2 | Define the KOVs | 1 | 2.4992 | 10.0563 | 12.5555 | 100 | 249.9216 | 1 | 2 | 4 | =F10 | =D11+E11
3 | Determine the Intermediate Outputs | 1 | 1.8379 | 10.0563 | 11.8942 | 100 | 183.7898 | 1 | 2 | 5 | =F10 | =D12+E12
4 | Design Complete Output Format | 2 & 3 | 7.4686 | 12.5555 | 20.0242 | 100 | 746.8648 | 3 | 5 | 10 | =MAX(F11,F12) | =D13+E13
5 | Validate Format on User | 4 | 6.6013 | 20.0242 | 26.6255 | 200 | 1320.2618 | 5 | 10 | 20 | =F13 | =D14+E14
6 | Define Input and Calculated Variables | 4 | 3.9252 | 20.0242 | 23.9494 | 100 | 392.518 | 2 | 3 | 6 | =F13 | =D16+E16
7 | Gather Primary Data | 6 | 223.1357 | 23.9494 | 247.0851 | 50 | 11156.7872 | 100 | 200 | 300 | =F16 | =D17+E17
8 | Gather Secondary Data | 6 | 14.9016 | 23.9494 | 38.8509 | 50 | 745.0788 | 10 | 15 | 30 | =F16 | =D18+E18
9 | Estimate Econometric Relations | 8 | 13.7977 | 38.8509 | 52.6487 | 150 | 2069.6573 | 10 | 30 | 60 | =F18 | =D19+E19
10 | Identify Stochastic Variables | 5 | 1.5779 | 26.6255 | 28.2034 | 150 | 236.6836 | 1 | 2 | 4 | =F14 | =D21+E21
11 | Gather Data for Stochastic Variables | 10 | 17.8899 | 28.2034 | 46.0932 | 50 | 894.4931 | 20 | 30 | 60 | =F21 | =D22+E22
12 | Parameter Estimation for Stochastic Variables | 11 | 8.656 | 46.0932 | 54.7493 | 150 | 1298.4067 | 5 | 10 | 20 | =F22 | =D23+E23
13 | Distribution Testing | 12 | 5.1322 | 54.7493 | 59.8815 | 200 | 1026.433 | 2 | 3 | 6 | =F23 | =D24+E24
14 | Assemble Model & Begin Testing | 7, 9 & 13 | 133.7153 | 247.0851 | 380.8004 | 250 | 33428.8314 | 50 | 100 | 200 | =MAX(F17,F19,F24) | =D26+E26
15 | Validation and Verification by: | 14 | 0 | 380.8004 | 380.8004 |  |  | 0 | 0 | 0 | =F26 | =D27+E27
16 | Personal | 15 | 40.4329 | 380.8004 | 421.2333 | 200 | 8086.5786 | 30 | 45 | 90 | =F27 | =D28+E28
17 | Peers | 15 | 98.3519 | 380.8004 | 479.1523 | 100 | 9835.1887 | 60 | 100 | 200 | =F27 | =D29+E29
18 | Producers | 15 | 53.8108 | 380.8004 | 434.6112 | 150 | 8071.6133 | 40 | 60 | 120 | =F27 | =D30+E30
19 | Model Refinement Based on Validation | 16, 17 & 18 | 37.4489 | 479.1523 | 516.6012 | 250 | 9362.2157 | 10 | 25 | 50 | =MAX(F28,F29,F30) | =D31+E31
20 | Model Application & Report Preparation | 19 | 11.1476 | 516.6012 | 527.7488 | 200 | 2229.5244 | 5 | 10 | 20 | =F31 | =D32+E32
[5 empty] | Days |  | Cost
Key Output Variables for Project Management |  |  |  | Total | 527.7488 | Total | 92340.48
1 DevelopDiagram
2 Define KOVs
3 Define Interm. Outputs
4 Define Full Output
7 Gather Primary Data
11 Get PDF Data
10 Id. Stoch. Variables
5 Validate Output
13 Test Distributions
12 PDF Parameter Estimation
14 Assemble the Model
8 Gather Secondary Data
9 Estimate Econometric
Relations
6 Define Inputs & Calculated
Variables
16 Personal
17
Peers
15 Model Validation
18 Producers
20 Model Application
19 Refine Model

## SimData
Simetar Simulation Results for 100 Iterations. 10:52:34 PM 12/21/2005 (0.72 sec.). © 2005.
Variable | Sheet1!F34 | Sheet1!H34
Mean | 495.2625 | 93778.9216
StDev | 72.3179 | 12304.5657
CV | 14.6019 | 13.1208
Min | 322.0405 | 70372.8445
Max | 717.1086 | 149778.5815
Iteration | Days | Cost
1 | 423.4978 | 70372.8445 | Days | CDFProb. | Cost | CDFProb.
2 | 482.4188 | 104320.173 | 322.0405 | 0 | 70372.8445 | 0
3 | 502.9242 | 91930.1252 | 347.1692 | 0.010101 | 75838.1448 | 0.010101
4 | 555.1884 | 94728.5145 | 348.2149 | 0.020202 | 76002.6049 | 0.020202
5 | 553.9554 | 94878.2563 | 357.765 | 0.030303 | 76026.695 | 0.030303
6 | 409.4596 | 79075.6415 | 374.2639 | 0.040404 | 76399.8489 | 0.040404
7 | 510.1535 | 102013.1744 | 391.0913 | 0.050505 | 77211.0246 | 0.050505
8 | 480.2575 | 89961.3954 | 404.1239 | 0.060606 | 77807.9138 | 0.060606
9 | 504.5158 | 106790.6441 | 405.3153 | 0.070707 | 77988.3259 | 0.070707
10 | 497.5607 | 94595.9159 | 409.4596 | 0.080808 | 78174.115 | 0.080808
11 | 590.539 | 97245.8802 | 410.3236 | 0.090909 | 78280.1442 | 0.090909
12 | 597.983 | 85746.5676 | 411.8674 | 0.10101 | 78783.999 | 0.10101
13 | 530.2611 | 97436.611 | 414.3606 | 0.11111 | 79075.6415 | 0.11111
14 | 419.9718 | 81658.6147 | 414.3995 | 0.12121 | 79272.1183 | 0.12121
15 | 544.4726 | 104981.986 | 419.9718 | 0.13131 | 80053.2553 | 0.13131
16 | 479.1091 | 90302.9538 | 423.4689 | 0.14141 | 80281.4705 | 0.14141
17 | 452.3206 | 105543.4695 | 423.4978 | 0.15152 | 81568.0393 | 0.15152
18 | 589.1373 | 109796.7772 | 425.5493 | 0.16162 | 81658.6147 | 0.16162
19 | 474.5228 | 99119.0452 | 427.0369 | 0.17172 | 81777.3497 | 0.17172
20 | 563.4062 | 106880.6045 | 428.5588 | 0.18182 | 82083.6824 | 0.18182
21 | 357.765 | 81568.0393 | 432.7378 | 0.19192 | 82409.6962 | 0.19192
22 | 542.9795 | 102157.6973 | 433.0069 | 0.20202 | 83137.562 | 0.20202
23 | 487.6979 | 98067.6179 | 434.9632 | 0.21212 | 83336.6263 | 0.21212
24 | 533.6561 | 95629.4657 | 435.8853 | 0.22222 | 83567.6558 | 0.22222
25 | 404.1239 | 86474.802 | 444.6357 | 0.23232 | 83709.8333 | 0.23232
26 | 560.9616 | 103129.1295 | 447.3787 | 0.24242 | 83988.4112 | 0.24242
27 | 455.1119 | 83709.8333 | 450.4665 | 0.25253 | 84207.9347 | 0.25253
28 | 507.2741 | 90688.1585 | 451.1834 | 0.26263 | 84211.1158 | 0.26263
29 | 673.7555 | 118123.1972 | 452.3206 | 0.27273 | 85746.5676 | 0.27273
30 | 548.7716 | 97178.2814 | 455.1119 | 0.28283 | 85940.4316 | 0.28283
31 | 433.0069 | 89372.4375 | 457.2076 | 0.29293 | 86474.802 | 0.29293
32 | 475.1527 | 105644.658 | 459.1794 | 0.30303 | 86967.5721 | 0.30303
33 | 478.219 | 77807.9138 | 460.3168 | 0.31313 | 87145.5293 | 0.31313
34 | 563.2918 | 106261.5277 | 460.4178 | 0.32323 | 88199.4564 | 0.32323
35 | 457.2076 | 95636.7778 | 462.9443 | 0.33333 | 89372.4375 | 0.33333
36 | 477.4799 | 89917.3751 | 463.781 | 0.34343 | 89689.3583 | 0.34343
37 | 578.9564 | 99753.9594 | 470.687 | 0.35354 | 89741.2593 | 0.35354
38 | 534.6598 | 94958.0437 | 470.7598 | 0.36364 | 89781.4002 | 0.36364
39 | 471.0239 | 97251.2543 | 471.0239 | 0.37374 | 89887.7034 | 0.37374
40 | 462.9443 | 98399.8015 | 471.6133 | 0.38384 | 89917.3751 | 0.38384
41 | 509.8636 | 107044.2498 | 474.5228 | 0.39394 | 89961.3954 | 0.39394
42 | 470.7598 | 102123.5962 | 475.1527 | 0.40404 | 90302.9538 | 0.40404
43 | 450.4665 | 86967.5721 | 476.7627 | 0.41414 | 90588.1107 | 0.41414
44 | 530.9746 | 100531.9261 | 477.4799 | 0.42424 | 90688.1585 | 0.42424
45 | 447.3787 | 78783.999 | 478.219 | 0.43434 | 90945.119 | 0.43434
46 | 482.3645 | 91644.7127 | 479.1091 | 0.44444 | 91279.8019 | 0.44444
47 | 498.9034 | 103361.0139 | 479.9997 | 0.45455 | 91540.6373 | 0.45455
48 | 444.6357 | 92275.2688 | 480.2575 | 0.46465 | 91644.7127 | 0.46465
49 | 470.687 | 78280.1442 | 482.3645 | 0.47475 | 91930.1252 | 0.47475
50 | 493.685 | 89887.7034 | 482.4188 | 0.48485 | 92275.2688 | 0.48485
51 | 661.9129 | 115649.5918 | 487.6979 | 0.49495 | 92757.5022 | 0.49495
52 | 531.4654 | 100171.0975 | 488.0539 | 0.50505 | 93993.9169 | 0.50505
53 | 555.4029 | 116401.6317 | 493.685 | 0.51515 | 94045.0702 | 0.51515
54 | 405.3153 | 83137.562 | 497.5607 | 0.52525 | 94104.7429 | 0.52525
55 | 374.2639 | 77211.0246 | 498.9034 | 0.53535 | 94595.9159 | 0.53535
56 | 410.3236 | 81777.3497 | 501.2755 | 0.54545 | 94728.5145 | 0.54545
57 | 391.0913 | 77988.3259 | 502.574 | 0.55556 | 94874.5353 | 0.55556
58 | 502.574 | 84207.9347 | 502.9242 | 0.56566 | 94878.2563 | 0.56566
59 | 536.3388 | 99144.222 | 504.3602 | 0.57576 | 94958.0437 | 0.57576
60 | 451.1834 | 94045.0702 | 504.5158 | 0.58586 | 95629.4657 | 0.58586
61 | 476.7627 | 76399.8489 | 507.2741 | 0.59596 | 95636.7778 | 0.59596
62 | 569.839 | 96697.4346 | 508.1056 | 0.60606 | 96697.4346 | 0.60606
63 | 471.6133 | 90588.1107 | 509.8636 | 0.61616 | 97045.4311 | 0.61616
64 | 511.6992 | 88199.4564 | 510.1535 | 0.62626 | 97077.5994 | 0.62626
65 | 432.7378 | 91540.6373 | 511.6992 | 0.63636 | 97178.2814 | 0.63636
66 | 411.8674 | 79272.1183 | 521.6383 | 0.64646 | 97245.8802 | 0.64646
67 | 603.1055 | 103234.9793 | 526.7033 | 0.65657 | 97251.2543 | 0.65657
68 | 347.1692 | 83567.6558 | 530.2611 | 0.66667 | 97436.611 | 0.66667
69 | 609.0599 | 104397.0715 | 530.9746 | 0.67677 | 98067.6179 | 0.67677
70 | 504.3602 | 89741.2593 | 531.4654 | 0.68687 | 98399.8015 | 0.68687
71 | 532.9843 | 109303.0923 | 532.9843 | 0.69697 | 98494.5625 | 0.69697
72 | 427.0369 | 78174.115 | 533.6561 | 0.70707 | 99119.0452 | 0.70707
73 | 556.3173 | 118318.6061 | 534.6598 | 0.71717 | 99144.222 | 0.71717
74 | 459.1794 | 83336.6263 | 536.3388 | 0.72727 | 99753.9594 | 0.72727
75 | 434.9632 | 82083.6824 | 541.0432 | 0.73737 | 100171.0975 | 0.73737
76 | 604.9453 | 92757.5022 | 542.9795 | 0.74747 | 100531.9261 | 0.74747
77 | 555.4355 | 80281.4705 | 544.4726 | 0.75758 | 101083.0343 | 0.75758
78 | 717.1086 | 149778.5815 | 548.7716 | 0.76768 | 102013.1744 | 0.76768
79 | 435.8853 | 89689.3583 | 549.1479 | 0.77778 | 102123.5962 | 0.77778
80 | 348.2149 | 85940.4316 | 553.9554 | 0.78788 | 102157.6973 | 0.78788
81 | 463.781 | 83988.4112 | 555.1884 | 0.79798 | 103129.1295 | 0.79798
82 | 414.3606 | 82409.6962 | 555.4029 | 0.80808 | 103234.9793 | 0.80808
83 | 541.0432 | 101083.0343 | 555.4355 | 0.81818 | 103361.0139 | 0.81818
84 | 423.4689 | 87145.5293 | 556.3173 | 0.82828 | 104320.173 | 0.82828
85 | 479.9997 | 97077.5994 | 560.9616 | 0.83838 | 104397.0715 | 0.83838
86 | 460.3168 | 76026.695 | 563.2918 | 0.84848 | 104981.986 | 0.84848
87 | 549.1479 | 94104.7429 | 563.4062 | 0.85859 | 105543.4695 | 0.85859
88 | 425.5493 | 94874.5353 | 569.839 | 0.86869 | 105644.658 | 0.86869
89 | 639.0402 | 122589.7705 | 578.4041 | 0.87879 | 106261.5277 | 0.87879
90 | 460.4178 | 91279.8019 | 578.9564 | 0.88889 | 106790.6441 | 0.88889
91 | 488.0539 | 89781.4002 | 584.3767 | 0.89899 | 106880.6045 | 0.89899
92 | 526.7033 | 107901.5953 | 589.1373 | 0.90909 | 107044.2498 | 0.90909
93 | 428.5588 | 84211.1158 | 590.539 | 0.91919 | 107901.5953 | 0.91919
94 | 414.3995 | 76002.6049 | 597.983 | 0.92929 | 109303.0923 | 0.92929
95 | 322.0405 | 75838.1448 | 603.1055 | 0.93939 | 109796.7772 | 0.93939
96 | 578.4041 | 97045.4311 | 604.9453 | 0.94949 | 115649.5918 | 0.94949
97 | 584.3767 | 93993.9169 | 609.0599 | 0.9596 | 116401.6317 | 0.9596
98 | 501.2755 | 80053.2553 | 639.0402 | 0.9697 | 118123.1972 | 0.9697
99 | 521.6383 | 98494.5625 | 661.9129 | 0.9798 | 118318.6061 | 0.9798
100 | 508.1056 | 90945.119 | 673.7555 | 0.9899 | 122589.7705 | 0.9899
|  |  | 717.1086 | 1 | 149778.5815 | 1
x1-value
Prob(X<=x1)
x2-value
Prob(X<=x2)
x3-value
Prob(X<=x3)
x4-value
Prob(X<=x4)
x5-value
Prob(X<=x5)